## Project Planner
Sea-Pix GAN
Project Deep Learning |  |  |  |  | Period Highlight: | 2 |  |  | Plan Duration |  | Actual Start | % Complete | Actual (beyond plan) | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5
read paper thoroughly | 1 | 1 | 1 | 1 | 100%
build skeleton encoder | 1 | 2 | 1 | 2 | 50%
build skeleton decoder | 1 | 2 | 1 | 2 | 50%
build skeleton discrimiator | 1 | 2 | 1 | 2 | 90%
train Generator on first dataset | 2 | 2 |  |  | 0%
train Discriminator on first dataset | 2 | 2 |  |  | 0%
train both on data and capture loss | 2 | 2 |  |  | 0%
Analyse results | 3 | 1 |  |  | 0%
reproduce figures from paper | 4 | 1 |  |  | 0%
make presentation | 4 | 1 |  |  | 0%
make github page | 4 | 1 |  |  | 0%
present | 5 | 1 |  |  | 0%
Activity 12 |  |  |  |  | 0%
Activity 13 |  |  |  |  | 0%
Activity 14 |  |  |  |  | 0%
Activity 15 |  |  |  |  | 0%
Activity 16 |  |  |  |  | 0%
Activity 17 |  |  |  |  | 0%
Activity 18 |  |  |  |  | 0%
Activity 19 |  |  |  |  | 0%
Activity 20 |  |  |  |  | 0%
Activity 21 |  |  |  |  | 0%
Activity 22 |  |  |  |  | 0%
Activity 23 |  |  |  |  | 0%
Activity 24 |  |  |  |  | 0%
Activity 25 |  |  |  |  | 0%
Activity 26 |  |  |  |  | 0%